## Project Detail
Project Code | Project Name | Portfolio | Hub | Project Type | Project Manager | Start Date | Contract Completion Date | Engineering % | Procurement % | Construction % | Modular Fabrication % | Commissioning %
KAZ.O.WO0009 | DP320 KAZ Flare C | South | KAZ (Khor Al Zubair) | EPC | Mohamed | 2022-11-14 | 2026-01-14 | 23 | 42 | 22.5 | 98 | 4.5

## Project Cost
Cut Off Date | Project Code | Original Budget (USD) | Approved Variations (USD) | Forecast At Completion (USD) | VOWD % | Allowances (USD)
2024-09-27 | KAZ.O.WO0009 | 80000 | 7600 | 50000 | 74 | 750

## Phase Progress
Cut Off Date | Project Code | Category | BI Code | Activity ID | Activity Description | Plan Progress % | Actual Progress %
2024-09-27 | KAZ.O.WO0009 | Engineering | COD_SRVC_PROG_ENG |  |  | 94.91 | 90.42
2024-09-27 | KAZ.O.WO0009 | Procurement | COD_SRVC_PROG_PROC |  |  | 97.76 | 87.92
2024-09-27 | KAZ.O.WO0009 | Construction | COD_SRVC_PROG_CONS |  |  | 20.12 | 14.27
2024-09-27 | KAZ.O.WO0009 | Modular Fabrication | COD_SRVC_PROG_MOD_FAB |  |  | 0 | 0
2024-09-27 | KAZ.O.WO0009 | COMMISSIONING | COD_SRVC_PROG_COM |  |  | 0 | 0

## Milestone Progress
Cut Off Date | Project Code | Category | BI Code | Activity ID | Activity Description | Plan Start Date | Plan End Date | Forecast Start Date | Forecast End Date | Actual Start Date | Actual End Date | LD %
2024-09-27 | KAZ.O.WO0009 | Milestone1 |  |  |  | 2019-01-04 | 2020-12-04 | 2019-01-04 | 2023-07-04 |  |  | 94.91
2024-09-27 | KAZ.O.WO0009 | Milestone2 |  |  |  | 2019-01-04 | 2021-05-04 | 2019-01-23 | 2023-06-04 |  |  | 97.76
2024-09-27 | KAZ.O.WO0009 | Milestone3 |  |  |  | 2019-02-08 | 2022-05-24 | 2019-01-30 | 2024-06-24 |  |  | 20.12
2024-09-27 | KAZ.O.WO0009 | Milestone4 |  |  |  | 2019-08-08 | 2023-06-14 | 2019-01-30 | 2024-02-16 |  |  | 0
2024-09-27 | KAZ.O.WO0009 | Milestone5 |  |  |  | 2020-11-28 | 2023-09-12 | 2022-12-12 | 2024-03-16 |  |  | 0

## Schedule
Cut Off Date | Project Code | Category | BI Code | Activity ID | Activity Description | Plan Start Date | Plan End Date | Forecast Start Date | Forecast End Date | Actual Start Date | Actual End Date | Plan Progress % | Actual Progress % | Is Key Activity
2024-09-27 | KAZ.O.WO0009 | Engineering | COD_SRVC_PROG_ENG |  |  | 2019-01-04 | 2020-12-04 | 2019-01-04 | 2023-07-04 |  |  | 94.91 | 90.42 | 0
2024-09-27 | KAZ.O.WO0009 | Procurement | COD_SRVC_PROG_PROC |  |  | 2019-01-04 | 2021-05-04 | 2019-01-23 | 2023-06-04 |  |  | 97.76 | 87.92 | 0
2024-09-27 | KAZ.O.WO0009 | Construction | COD_SRVC_PROG_CONS |  |  | 2019-02-08 | 2022-05-24 | 2019-01-30 | 2024-06-24 |  |  | 20.12 | 14.27 | 0
2024-09-27 | KAZ.O.WO0009 | Modular Fabrication | COD_SRVC_PROG_MOD_FAB |  |  | 2019-08-08 | 2023-06-14 | 2019-01-30 | 2024-02-16 |  |  | 0 | 0 | 0
2024-09-27 | KAZ.O.WO0009 | COMMISSIONING | COD_SRVC_PROG_COM |  |  | 2020-11-28 | 2023-09-12 | 2022-12-12 | 2024-03-16 |  |  | 0 | 0 | 0
2024-09-27 | KAZ.O.WO0009 | Milestone1 |  |  |  | 2019-01-04 | 2020-12-04 | 2019-01-04 | 2023-07-04 |  |  |  |  | 1
2024-09-27 | KAZ.O.WO0009 | Milestone2 |  |  |  | 2019-01-04 | 2021-05-04 | 2019-01-23 | 2023-06-04 |  |  |  |  | 1
2024-09-27 | KAZ.O.WO0009 | Milestone3 |  |  |  | 2019-02-08 | 2022-05-24 | 2019-01-30 | 2024-06-24 |  |  |  |  | 1
2024-09-27 | KAZ.O.WO0009 | Milestone4 |  |  |  | 2019-08-08 | 2023-06-14 | 2019-01-30 | 2024-02-16 |  |  |  |  | 1
2024-09-27 | KAZ.O.WO0009 | Milestone5 |  |  |  | 2020-11-28 | 2023-09-12 | 2022-12-12 | 2024-03-16 |  |  |  |  | 1

## Project Schedule (2) (hidden)
Cut Off Date | Project Code | Category | BI Code | Activity ID | Activity Description | Plan Start Date | Plan End Date | Forecast Start Date | Forecast End Date | Actual Start Date | Actual End Date | Plan Progress % | Actual Progress % | Is Key Milestone
2024-09-27 | PROJECT_COD_01 | Engineering | COD_SRVC_PROG_ENG |  |  | 2019-01-04 | 2020-12-04 | 2019-01-04 | 2023-07-04 |  |  | 94.91 | 90.42 | 0
2024-09-27 | PROJECT_COD_01 | Procurement | COD_SRVC_PROG_PROC |  |  | 2019-01-04 | 2021-05-04 | 2019-01-23 | 2023-06-04 |  |  | 97.76 | 87.92 | 0
2024-09-27 | PROJECT_COD_01 | Construction | COD_SRVC_PROG_CONS |  |  | 2019-02-08 | 2022-05-24 | 2019-01-30 | 2024-06-24 |  |  | 20.12 | 14.27 | 0
2024-09-27 | PROJECT_COD_01 | Modular Fabrication | COD_SRVC_PROG_MOD_FAB |  |  | 2019-08-08 | 2023-06-14 | 2019-01-30 | 2024-02-16 |  |  | 0 | 0 | 0
2024-09-27 | PROJECT_COD_01 | COMMISSIONING | COD_SRVC_PROG_COM |  |  | 2020-11-28 | 2023-09-12 | 2022-12-12 | 2024-03-16 |  |  | 0 | 0 | 0
2024-09-27 | PROJECT_COD_01 | Milestone1 |  |  |  | 2019-01-04 | 2020-12-04 | 2019-01-04 | 2023-07-04 |  |  |  |  | 1
2024-09-27 | PROJECT_COD_01 | Milestone2 |  |  |  | 2019-01-04 | 2021-05-04 | 2019-01-23 | 2023-06-04 |  |  |  |  | 1
2024-09-27 | PROJECT_COD_01 | Milestone3 |  |  |  | 2019-02-08 | 2022-05-24 | 2019-01-30 | 2024-06-24 |  |  |  |  | 1
2024-09-27 | PROJECT_COD_01 | Milestone4 |  |  |  | 2019-08-08 | 2023-06-14 | 2019-01-30 | 2024-02-16 |  |  |  |  | 1
2024-09-27 | PROJECT_COD_01 | Milestone5 |  |  |  | 2020-11-28 | 2023-09-12 | 2022-12-12 | 2024-03-16 |  |  |  |  | 1

## Man Power
Cut Off Date | Project Code | Category | Type | 2024-06-28 | 2024-07-26 | 2024-08-30 | 2024-09-27 | 2024-10-25 | 2024-11-29 | 2024-12-27 | 2025-01-31 | 2025-02-28 | 2025-03-28 | 2025-04-25 | 2025-05-30
2024-09-27 | KAZ.O.WO0009 | Engineering | P | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
2024-09-27 | KAZ.O.WO0009 | Engineering | F | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
2024-09-27 | KAZ.O.WO0009 | Engineering | A | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
2024-09-27 | KAZ.O.WO0009 | PMT | P | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
2024-09-27 | KAZ.O.WO0009 | PMT | F | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
2024-09-27 | KAZ.O.WO0009 | PMT | A | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32
2024-09-27 | KAZ.O.WO0009 | CMT | P | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35
2024-09-27 | KAZ.O.WO0009 | CMT | F | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38
2024-09-27 | KAZ.O.WO0009 | CMT | A | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43
2024-09-27 | KAZ.O.WO0009 | S/C's | P | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32
2024-09-27 | KAZ.O.WO0009 | S/C's | F | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57
2024-09-27 | KAZ.O.WO0009 | S/C's | A | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65

## Man Power (2) (hidden)
Cut Off Date | Project Code | Category | Month Cut Off Date | Plan | Actual
2022-09-30 | PROJECT_COD_01 | Engineering |  | 10 | 7
2022-09-30 | PROJECT_COD_01 | PMT
2022-09-30 | PROJECT_COD_01 | CMT
2022-09-30 | PROJECT_COD_01 | S/C's
2022-09-30 | PROJECT_COD_01
2022-09-30 | PROJECT_COD_01
[5 empty] | M1 | M2 | M3
|  | Engineering |  | Plan | 15 | 25 | 45
Actual
|  | PMT |  | Plan
Actual
|  | CMT |  | Plan
Actual
|  | S/C's |  | Plan
Actual

## Risk (2) (hidden)
Cut Off Date | Project Code | Risk Type | Risk Count | Contractual Finish Date | P80 | P50 | P10
2022-09-30 | PROJECT_COD_01 | Approved | 1 | 2028-01-01 | 2028-03-30 | 2028-02-01 | 2028-01-15 | M1
2022-09-30 | PROJECT_COD_01 |  |  |  | 89 | 31 | 14
2022-09-30 | PROJECT_COD_01 |  |  |  | 2028-04-15 | 2028-01-20 | 2028-01-05 | M2
2022-09-30 | PROJECT_COD_01 |  |  |  | 105 | 19 | 4
2022-09-30 | PROJECT_COD_01
2022-09-30 | PROJECT_COD_01

## Risk
Cut Off Date | Project Code | Risk Stage | Completion Date
2024-09-27 | KAZ.O.WO0009 | P80 | 2028-03-30
2024-09-27 | KAZ.O.WO0009 | P50 | 2028-02-01
2024-09-27 | KAZ.O.WO0009 | P10 | 2028-01-15

## Variations
Cut Off Date | Project Code | Variation Status | Variation Count | Variation Cost
2024-09-27 | KAZ.O.WO0009 | Submitted | 10 | 100000000
2024-09-27 | KAZ.O.WO0009 | Approved | 2 | 30000000
2024-09-27 | KAZ.O.WO0009 | Under-review | 3 | 20000000
2024-09-27 | KAZ.O.WO0009 | Rejected | 5 | 50000000
2024-09-27 | KAZ.O.WO0009 | Anticipated | 6 | 60010000

## HSE
Cut Off Date | Project Code | HSE Type | HiPo | Fatalities | Near Miss | Near Miss Frequency Rate | Cumulative Hours | LTI Free Hours
2024-09-27 | KAZ.O.WO0009 | PTD | 0 | 0 | 5 | 0.19 | 5520000 | 2760000
2024-09-27 | KAZ.O.WO0009 | YTD |  |  |  |  | 876000 | 500000

## Quality
Cut Off Date | Project Code | Quality Category | Total | Closed
2024-09-27 | KAZ.O.WO0009 | CAR | 150 | 120
2024-09-27 | KAZ.O.WO0009 | NCR | 15 | 18

## Area Of Focus
Cut Off Date | Project Code | Discipline | Remarks
2024-09-27 | KAZ.O.WO0009 | CAR | Using a format string as I've done here, the underlying data is not changed - you can see in the image above that the Data type still says it is Date/time
2024-09-27 | KAZ.O.WO0009 | Engineering | What's the version of your PBI Desktop? I tried Phil's file with 2.128.952.0 64-bit (April 2024) without any date format problem.